## Sheet1
Agile Project Risk Register
Risk | Probability (%) | Impact in days | Exposure in days
Proof of concept is inconclusive (example) | 50% | 10 | 5
Inability to communicate between mobile and legacy systems (example) | 25% | 30 | 7.5
| 0% | 0 | 0
| 0% | 0 | 0
| 0% | 0 | 0
| 0% | 0 | 0
| 0% | 0 | 0
| 0% | 0 | 0
| 0% | 0 | 0
| 0% | 0 | 0
| 0% | 0 | 0
| 0% | 0 | 0
Total Exposure |  |  | 12.5